## 1) Deckblatt (hidden)
Verlagerung
Deckblatt
Berichtsnr.: | Risikomanagement Tool |  |  | Datum: | JJJJ-MM-TT |  | Teil: 1
Firma: |  |  | Antragsteller: |  | Name, Vorname
Analysegrund:
Werk:
Strasse: |  |  | Homepage / URL:
PLZ / Ort: |  |  | DUNS-Nummer / Link
Land: |  |  | Lieferantennummer:
Branchennr.: |  |  | Branchenname:
Datum
|  | Gate 0 (RLA) / date |  |  | EG = | r/g | % | A
|  | Gate A / date |  |  | EL = | r/g | % | A
|  | Gate B / date |  |  | EH= | r/g | % | A
|  | Gate C / date |  |  | EQ= | r/g | % | A
%
Produkt- / Produktgruppe:
Anmerkungen
Verantwortlich
Gate 0
o
Gate A
o
Gate B
o
Gate C
o
Analyse Team
Name, Vorname |  | Name, Vorname |  |  | Name, Vorname
PL |  | Auditor abgebender Standort |  |  | Auditor aufnehmender Standort
Verteiler: |  |  | Name / Abt. |  |  | Name / Abt.
Anforderer: | Name, Vorname |  | Name / Abt. |  |  | Name / Abt.
Team | Name, Vorname |  | Name / Abt. |  |  | Name / Abt.
| Name, Vorname |  | Name / Abt. |  |  | Name / Abt.
| Name, Vorname |  | Ablage: SP/HZA-M
Note on D19: Bewertung erfolgt ausschließlich durch CM

## Überblick (hidden)
Verlagerung
|  | Genehmigungsphase |  | Verlagerungsvorbereitung |  | Verlagerungsdurchführung |  | Lessons learned
| Gate 0: Beantraung einer Verlagerung |  | Gate A Projektvorbereitung |  | Gate B: Abgebendes Werk |  | Gate C: aufnehmendes Werk |  | Gate D: Abschluß
|  | Aktivität Schaeffler |  | Aktivität Schaeffler |  | Aktivität Schaeffler |  | Aktivität Schaeffler
| Lieferant teilt Absicht mit, verlagern zu wollen | Entscheidung über Verlagerung bzw. Vorbedingung | Antrag wird seitens Schaeffler statt gegeben | Entscheidung über geeingete Maßnahmen und deren Verfolgung | Audit im abgebenden Werk | Entscheidung über geeingete Maßnahmen und deren Verfolgung | Audit im aufnehmenden Werk | Entscheidung über geeingete Maßnahmen und deren Verfolgung | Feedback und Abschlußgespräch 7 Beurteilungsbogen
t

## Phase 1 - Transfer Planning
Quality Assurance Agreement with Production Material Suppliers
Checklist for Production Transfers: Phase 1 - Transfer Planning
Supplier |  | Date (YYYY-MM-DD)
Responsible |  | Product / Product group
8
No. | Question | Determination / Verification | Status | Containment action | Responsible / Date | Stand in % |  |  |  |  | 4
[6 empty] | 20 | 40 | 60 | 80 | 100 | n.b.
A1 | Project management
A 1.1 | Is the project manager and the project / relocation team nominated at delivering and receiving plant and are their competencies clearly regulated ? Necessary disciplines / departments are e.g. logistics, process engineering, QA, purchasing, manufacturing
A 1.2 | Are the targets of the project defined ? - cost - time line (incl. SOP) - cost of relocation
A 1.3 | Is a complete project plan existing including due dates, responsibilities, all APQP questions according APQP check list, etc ?
A 1.4 | Logistics planning of products: - extended transport time, buffer stock, modified packaging / rust-proofing
A 1.5 | Was the risk of the relocation analysed by the supplier (relocation RLA) ? | [10 empty] | 10
A 1.6 | Is a layout plan existing for the receiving plant?
A 1.7 | Is a training concept existing for all employees affected by the relocation ?
A 1.8 | Are the necessary release tests coordinated with the customer ?
A 1.9 | Are the expenses for the tests coordinated with the customer ?
A 1.10 | Is the initial sample inspection coordinated with the customer ?
A2 | Safe transfer | [10 empty] | 6
A 2.1 | Are there deviations between delivering and receiving plant (machines, devices / fixtures / tools, flow chart, control plan, failure prevention actions) ? | [10 empty] | 0
A 2.2 | Are there changes at the subsuppliers, and are they coordinated with the customer (suppliers for semi-finished products and external processes like heat treatment, surface coatings, etc.) ?
A 2.3 | Are all necessary measuring and testing devices available at the receiving plant ?
A 2.4 | Are all customer demands reliable covered for the time between start of relocation until SOP at the receiving plant (preproduction, emergency plan, fall-back solution) ? | [10 empty] | n.b.
A 2.5 | Are all characteristics defined where a process capability has to be verified ?
A 2.6 | Are the drawings and SC/CC characteristics known in the receiving plant ? Are drawing changes maybe necessary at the part numbers planned for relocation ? | [10 empty] | ?
A 2.7 | How is it assured / guaranteed that parts of existing production and parts after relocation can be differentiated (batch traceability) ?
A3 | Customer focus
A 3.1 | Are the Schaeffler requirements (QAA, feasibility confirmation, etc.) known, existing and confirmed in writing at the receiving plant ?
A 3.2 | Is the application known at the receiving plant ?
A 3.3 | Are additional inspections for the start-up phase after the relocation agreed with the customer (e.g. 100% inspection at restart) ?
A 3.4 | Is there an application for modification approval for every single material number ?
A 3.5 | Are qualified contact persons, with good knowledge of the national language and additional german or english language, available at the receiving plant ? | [10 empty] | 10
[6 empty] | 0 | 0 | 0 | 0 | 0 |  | n.b.
Dieses Dokument wird als elektronische Datei gehandelt - gilt ohne Unterschrift | [11 empty] | ?
10
6
4
n.b.
?

## Phase 2 - Delivering Plant
Quality Assurance Agreement with Production Material Suppliers
Checklist for Production Transfers: Phase 2 - Delivering Plant
Supplier |  | Date (YYYY-MM-DD)
Responsible |  | Product / Product group
8
No. | Question | Determination / Verification | Status | Containment action | Responsible / Date | Stand in % |  |  |  |  | 4
[6 empty] | 20 | 40 | 60 | 80 | 100 | n.b.
B1 | Project management
B 1.1 | Is the project plan (including dates and responsibilities) consistently tracked and updated (including all APQP questions) ?
B 1.2 | Are project targets and milestones kept so far ? - buffer stock - new production place available - corrective maintenance - further
B 1.3 | Have trainings taken place at the delivering plant for all employees affected by the relocation ?
B 1.4 | Was the efficiency of the trainings certified ?
B2 | Safe relocation | [10 empty] | 10
B 2.1 | Has the supplier conducted an internal relocation audit for product and process, and are corrective actions defined ?
B 2.2 | Are reference parts deposited and completely measured for measuring calibration with the receiving plant ?
B 2.3 | Is the process capability / scrap rate and rework rate determined at the delivering plant ?
B3 | Documentation completely and prepared for transfer to the receiving plant
B 3.1 | Are all current drawings, standards, technical delivery conditions, packaging specifications, quality assurance agreement, etc. transferred to the receiving plant ?
B 3.2 | Are the necessary product documents (PPAP, FMEA, control plan, work instructions, etc.) completely available and transferred to the receiving plant? | [10 empty] | 6
B 3.3 | Are all failure prevention actions (e.g. by present quality deviations / complaints) transferred to the receiving plant ? | [10 empty] | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 |  | n.b.
Dieses Dokument wird als elektronische Datei gehandelt - gilt ohne Unterschrift | [11 empty] | ?
10
6
4
n.b.
?

## Phase 3 - Receiving Plant
Quality Assurance Agreement with Production Material Suppliers
Checklist for Production Transfers: Phase 3 - Receiving Plant
Supplier |  | Date (YYYY-MM-DD)
Responsible |  | Product / Product group
8
No. | Question | Determination / Verification | Status | Containment action | Responsible / Date | Stand in % |  |  |  |  | 4
[6 empty] | 20 | 40 | 60 | 80 | 100 | n.b.
C1 | Project management
C 1.1 | Is the project plan (including dates and responsibilities) consistently tracked and updated (including all APQP questions) ?
C 1.2 | Are the project targets and milestones kept so far and are possibly actions defined and tracked ?
C 1.3 | Is a start-up assistance by the delivering plant in place ?
C 1.4 | Have trainings taken place at the delivering plant for all employees affected by the relocation ? Are training certificates available ?
C 1.5 | Is the application known ? | [10 empty] | 10
C2 | Safe relocation
C 2.1 | Are all necessary measuring and testing devices in use at the receiving plant ? Are there changes compared to the delivering plant ?
C 2.2 | Has the supplier conducted an internal relocation audit for product and process at the receiving plant, and are corrective actions, responsibilities and dates defined ?
C 2.3 | Are comparative measurements with the reference parts done, is the measuring calibration completely done and is the result evaluated ?
C 2.4 | Are the corrective actions of the internal relocation audit systematically implemented ?
C 2.5 | Is the process capability / scrap rate and rework rate of the receiving plant the same as at the delivering plant or better ? | [10 empty] | 6
C 2.6 | Are the production capacities including purchase of semi-finished products applicable to fulfil Schaeffler's demands (e.g. check with Run @ Rate) ? | [10 empty] | 0
C3 | Documentation of receiving plant
C 3.1 | Are the current drawings including agreed SC/CC characteristics, standards, customer specifications, technical delivery conditions, packaging specifications and quality assurance agreement available and confirmed in writing at the receiving plant ?
C 3.2 | Are the necessary product documents (PPAP, FMEA, work instructions, etc.) completely available ? | [10 empty] | n.b.
C 3.3 | Are all failure prevention actions of the delivering plant (e.g. by present quality deviations / complaints) known and implemented at the receiving plant ?
C 3.4 | Are inspection instructions, work instructions, process instructions in national language in place at the work stations ? Are SC/CC characteristics specially marked ? | [10 empty] | ?
C 3.5 | Are the initial sample inspection documents completely available at the receiving plant ?
C 3.6 | Are PPAP documents like e.g. process flow chart, control plan, process capability study, FMEA complete and updated at the receiving plant ?
C 3.7 | Are the necessary release tests successfully finished ?
C 3.8 | Is the initial sample inspection released by the customer ?
C 3.9 | Are the present complaints (failures) known and the failure prevention actions on site implemented ?
C 3.10 | Are the additional inspections conducted as agreed (e.g. 100% inspection at restart) ?
C4 | Logistics | [10 empty] | 10
C 4.1 | Is packaging and rust-proofing modified according to the different transport conditions ? | [10 empty] | n.b.
C 4.2 | Is the agreed safety buffer available ? | [10 empty] | ?
Dieses Dokument wird als elektronische Datei gehandelt - gilt ohne Unterschrift
10
6
4
n.b.
?